## Sheet1
Story ID | Story Name | Description | Priority | Iteration number | Acceptance Criteria | Notes | Date started | Date finished
1 | Program root directory. | As a developer, you can obtain the root directory path of the program during runtime to store project files in a dedicated folder within it. | Must have | 1 | 1.Return the absolute path of the project's runtime root directory. | Functional requirement | 2023-03-27 | 2023-03-31
2 | Sidebar and main content area. | As a user, I would like to have the ability to quickly switch between different pages by clicking on the sidebar in the software. This feature simplifies navigation and makes it convenient to access different content. | Must have | 1 | 1.Complete the sidebar where clicking on it allows switching between different content, such as Course, Internship, Research, Work, etc. | Functional requirement | 2023-03-27 | 2023-03-31
3 | Cache | As a developer, I would like to have the ability to perform temporary in-memory caching during the runtime of the program, in order to temporarily store some information during program execution. | Must have | 1 | 1.Can store key-value pairs. 2.Can retrieve the corresponding value by key. 3.Can remove a key-value pair by key. 4.Can check if a specific key-value pair is currently stored. 5.Can get the current count of stored key-value pairs. 6.Can clear all key-value pairs. 7.Can output all currently stored key-value pairs. | Functional requirement | 2023-03-27 | 2023-03-31
4 | Add, delete, modify and check files and folders | As a student, I want to be able to create structured folders and be able to place files underneath them so that I can manage my documents in a structured way | Should have | 2 | 1. Given a path, recursively create the folder 2. Given a path, delete the file or recursively delete the folder 3. Set the path of the current file and the specified path, and move the current file to the specified location 4. Given a path, check whether the file or folder exists 5. Given a path, return all files in the current path as the root node | Functional requirement | 2023-04-03 | 2023-04-14
5 | Display information and read and write JSON files | As a student, I want to be able to store some information into a local file or read some information in a local file so that I can manage it | Should have | 2 | 1. Store the Java object in a Json file in the specified Path 2. Read the JSON file and obtain the corresponding Java object | Functional requirement | 2023-04-03 | 2023-04-14
6 | Create and destroy Modules | As a student, I want to be able to personalize my LearningJourney, add or remove my own modules, so that I can manage my own module information | Should have | 2 | 1. You can create any entity class object with corresponding properties and method 2. You can destroy any entity object | Functional requirement | 2023-04-03 | 2023-04-14
7 | Course document management | As a student, I want to be able to manage my course files so that I can record my class notes, coursework, courseware, lab projects, etc | Should have | 2 | 1. In the course interface, create a "Class Notes" subsection 2. Create a "Coursework" subsection 3 under the course interface. Create a "Lab Project" subsection in the Course Interface 4. Create a "Course Materials" subsection in the course interface 5. Each section supports adding and deleting files | Functional requirement | 2023-04-03 | 2023-04-14
8 | Course score calculation | As a student, I would like to be able to input the weights and scores for each section of a course to calculate the final score for that course | Could have | 3 | 1. Input the score and weight of each part of the course, ensure that the total weight is 1, and calculate the final score of the course | Functional requirement | 2023-04-17 | 2023-04-28
9 | Course information display | As a student, I hope to display my course information. It is better to display the brief information on the main interface, so that I can intuitively view the main information about the course. | Could have | 3 | 1. Add an area to the course homepage to display the main information, including course name, course number, lecturer, credits, course type, teacher contact information, grade (if any), etc | Functional requirement | 2023-04-17 | 2023-04-28
10 | Course statistics | As a student, I hope to show the statistical information of all courses, so that I can visually view all courses and obtain the average score of courses, GPA and other relevant information. | Could have | 3 | 1. Add the statistical information button on the course homepage. Click to view the statistical information table of the course, including course number, course name, course score, etc 2. The course statistics table can be changed by double-clicking and can be saved to a local csv file 3. You can load the local csv file to display the data | Functional requirement | 2023-04-17 | 2023-04-28
11 | Menu bar | As a user, I want to have a menu bar in the software so that I can quickly access various functions and operations of the application | Want to have | 4 | 1. Complete the menu bar and provide different services, such as file import and export, view user manual, view project repository, etc | Functional requirement | 2023-05-01 | 2023-05-12
12 | Check the User Manual | As a user, I want to be able to quickly open the user manual in the interface, so that I can view the operation process of the interface | Want to have | 4 | 1.Help-Help Open the User Manual file and view the user guide for all interfaces | Functional requirement | 2023-05-01 | 2023-05-12
13 | Export project file | As a user, I want to be able to compress and store the project files conveniently, so that I can back up and save all the files of the project | Want to have | 4 | 1. File-export Compress and Export the project File and select a storage path | Functional requirement | 2023-05-01 | 2023-05-12
14 | Open the file manager at the root of the project | As a user, I want to be able to open a folder in the interface where the program is stored so that I can manage all the files | Want to have | 4 | 1. File-open Open the File manager in the root directory of the project file | Functional requirement | 2023-05-01 | 2023-05-12
15 | Curve display | As a student, I hope to show the changes of scores and other information in each semester in the form of line charts, so as to visually show the changes of scores, credits and ranking with each semester | Want to have | Next iteration | 1. Add a new graph to the statistical information page, which can draw a curve according to the changes of average score, credits and ranking of each academic year. | Functional requirement
16 | Drag and drop a new course item | As a student, I would like to be able to create a new course by dragging and dropping all the materials of the course, in order to simplify the operation of input information required for creating a new course | Want to have | Next iteration | 1. Drag and drop a folder to obtain the folder path 2. According to the path and the files in the path, obtain the course information and create a course | Functional requirement
17 | Course score detail management | As a student, I hope to be able to display and modify my course scores, including total score, grade point, grade composition, etc., so that I can review my scores | Want to have | Next iteration | 1. Create a score plate in the course interface and click it to display the score table, which can show the score of this course 2. You can edit and modify the file in the table, and save the modified file to a local file | Functional requirement
18 | Course information modification | As a student, I hope to manage and modify the main information and other information of this course on the interface, so as to facilitate the management of information about this course | Want to have | Next iteration | 1. Double-click on the course details page to modify the course information and save it to a local file | Functional requirement
19 | Look at the average score and GPA | As a student, I hope that the program can calculate and display the average score and GPA based on the scores of all the courses that have been added, so that I can check my current average score and GPA | Want to have | Next iteration | 1. Display the current average score and GPA in the statistics popup on the course homepage | Functional requirement
20 | Add, delete, correct and check the curriculum items | As a student, I hope to manage my courses, so I need to be able to add, delete, modify and query course objects, so that I can manage them better. | Want to have | Next iteration | 1. Add a search bar to the course homepage to search for courses 2. Add the "add" bar on the course homepage, and you can add courses after entering the detailed information about the course 3. Add the Delete key in the right-click menu to delete the course object | Functional requirement